## Sheet1
Title | Domain | Name | Description | TimelineStart | TimelineEnd | Status | Priority | Owner | Teams | Link | Progress
PLAT-1 | platform | Auth revamp | Replace legacy auth with SSO and MFA across all apps. | 2026-01-12 | 2026-03-28 | In Progress | High | Jane Doe | core | https://example.com/projects/plat-1 | 45
PLAT-2 | platform | API gateway | Centralize routing, rate limiting, and observability. | 2026-03-02 | 2026-06-30 | Future | Medium | Sam Lee | core,data |  | 0
PLAT-3 | platform | Cost optimization | Right-size infrastructure and cut idle spend. | 2026-07-01 | 2026-09-15 | At Risk | High | Priya N. | core |  | 10
MKT-1 | marketing | Brand refresh | New visual identity, logo, and site theme. | 2026-02-01 | 2026-04-30 | Close to done | Medium | Alex Park | design | https://example.com/projects/mkt-1 | 80
MKT-2 | marketing | Q3 campaign | Multi-channel launch campaign for the new release. | 2026-06-15 | 2026-09-30 | Future | Low | Jordan Kim | design,data |  | 0
MOB-1 | mobile | Offline mode | Local caching and sync for spotty connectivity. | 2026-01-20 | 2026-05-10 | In Progress | High | Chris Wong | core,qa |  | 55
MOB-2 | mobile | Accessibility pass | WCAG AA audit and remediation across screens. | 2026-05-01 | 2026-07-31 | Done | Medium | Robin Shah | design,qa |  | 100